Multi-Year Accessibility Plan

2022 - 2025

for

The Dryden Regional Health Centre

This publication is available on the following website:

www.drhc.on.ca

# AODA – Statement of Commitment to Accessibility

Dryden Regional Health Centre is committed to providing a barrier-free environment for all stakeholders including our clients/customers, employees, job applicants, suppliers, and any visitors who may enter our premises, access our information, or use our services. As an organization, we respect and uphold the requirements set forth under the Accessibility for Ontarians with Disabilities Act (2005), and its associated standards and regulations.

Dryden Regional Health Centre understands that we have a responsibility for ensuring a safe, dignified, and welcoming environment for everyone. We are committed to ensuring our organization's compliance by incorporating accessibility legislation into our policies, procedures, equipment requirements, training, and best practices. We will review these policies and practices annually, as organizational changes occur, or in anticipation of compliance deadlines. In addition, we will strive to meet the needs of individuals with disabilities in a timely and effective manner.

Providing an accessible and barrier-free environment is a shared effort, and as an organization, Dryden Regional Health Centre is committed to working with the necessary parties to make accessibility for all a reality. For more detailed information on our accessibility policies, plans, and training programs, please contact AODA Office at 223-8201 ext.2268.

Regards,

Doreen Armstrong - Ross

Chief Executive Officer

Dryden Regional Health Centre

Executive Summary

The Integrated Accessibility Standards Regulation (IASR) of AODA became law in June 2011, and requires hospitals to produce multi-year accessibility plans that include targets and timelines for compliance with the multiple requirements of the IASR, in addition to their activities relating to both the Customer Service Standard and locally identified barriers in by-laws, policies, programs, practices and services

Since 2010, the Dryden Regional Health Centre (DRHC) has prepared an annual accessibility plan that addresses the identification, removal, and prevention of barriers for persons with disabilities, in keeping with the Ontarians with Disabilities Act (ODA 2001).

In this, the DRHC Multi-Year Accessibility Plan 2022 – 2025, you will find references to the Accessibility for Ontarians with Disabilities Act (AODA 2005), which builds on the ODA and whose purpose is to create an accessible Ontario by 2025 through the development of standards and enforcement mechanisms.

In keeping with AODA and IASR, this plan was created in consultation with our DRHC Accessibility Committee, including representatives from DRHC, and external stakeholders.

The DRHC is committed to ensuring that all staff are trained in customer service as it relates to accessibility on orientation and ongoing through annual education.

DRHC is committed to providing equal treatment to people with disabilities with respect to the use and benefit of services, programs, goods, and facilities.  We are committed to giving people with disabilities the same opportunity to access services and to allowing them to benefit from the same services as all other patients, clients, and employees.  This commitment extends to patients, clients, families, visitors, employees, physicians, and volunteers with visible and non-visible disabilities.

This plan is available in alternate format, or with communication support, upon request.

Please address your questions and concerns to:

Dryden Regional Health Centre

AODA Office

Attn: Katherine Campbell

58 Goodall Avenue, P.O. Box 3003

Dryden, ON P8N 2Z6

Website: www.drhc.on.ca

| BARRIER TYPE | Location | DESCRIPTION OF BARRIER | STRATEGY to ADDRESS | LEAD PERSON/ PROGRESS | Timeline/ Status |
| --- | --- | --- | --- | --- | --- |
| 2017-2021 plan results |  |  |  |  |  |
| Communication | Organization - wide | Requirement for organization communication tool that supports individuals with visual and hearing impairments | Implement Vocera across the organization. Improves communication across the organization. | Manager, IT | Complete – Vocera has been implemented across the organization |
|  | Organization – wide | Reviewed the external internet page for accessibility during an update process | External internet page has been overhauled completely and features the ability to translate, increase font size, reading capability, and change backgrounds for those visual impaired. | Communication and Board Liaison/ Manager, IT | April 2022 |
|  | Organization – wide | Emergency and public safety information available throughout the organization for staff and patients/family/visitors. Linked to workplace emergency information standard | Emergency codes: develop staff and patient education resources Patient handbook – developed with emergency information for public safety Resources available in an accessible format or with communication supports upon request. | Director, Risk, Safety, Quality/ Stakeholder Engagement & Relations | Staff and patient emergency codes resources have been completed. |
|  | Organization – wide | Printed and digital materials are reviewed for legibility of text and the contrast of visual elements, such as graphical controls and visual indicators. | Review current patient and staff education or resources for colour contrast. Education and training provided to management team to ensure compliant with colour contrast. | Occupational Therapist Director, Rehab | Complete. Ongoing as new materials are produced. |
|  | Organization – wide | Ensure clear directional signage and general signage are tactile, low vision appropriate and at a uniform height throughout the building (s) | Review legislation requirements Audit facilities and develop plan for updating signage | Director, Facilities | Ongoing as new renovations are complete each year. |
| Human Resources | Organization - wide | Access to mental health resources and supports for staff | Review the need to expand the availability of the Mental Health First Aid Training available for staff | Director, Human Resources and Clinical Information | Complete. Management staff have been trained in Mental Health First Aid Training. Lifeworks has been made available to all staff – MH/EAP program. |
|  | Organization - wide | Attendance program supports staff living with disabilities | Review attendance program ensuring adherence to accessibility legislation | Director, Human Resources and Clinical Information | Compete. Program has been updated. |
| Physical Environment | Organization - wide | Curb, front entrance Walkways – from parking lot to curbs Difficult for persons with limited vision to distinguish curb height | Paint curbs with yellow fluorescent paint | Director, Facilities | Complete: annually |
|  | Organization- wide | Reviewed the requirement for patients, visitors, and families to self-screen upon entering the facility | Implement self-screening kiosks at entrances for patients, families, and visitors | Director, Facilities | Complete – Spring 2022 |
|  | DRHC – Inpatient Unit/ Emergency Department | Review locations for additional accessible door access buttons | 5 locations were updated with wheelchair accessibility buttons: - 2 Emergency Department - 2 Inpatient Unit/East Unit - 1 main hallway leading from East Unit | Director, Facilities | Complete |
|  | DRHC – Inpatient Unit | Tub room: Sink inaccessible to wheelchair Automated tub and chair: accessible | Audit accessibility of tub room Replace sink with accessible unit | Director, Facilities /Finance/ In-patient- Emergency Services | Complete. |
|  | DRHC – Inpatient Unit/ Emergency Department | Determine what bariatric equipment is required for Inpatient Unit (East Unit) and/or Emergency Department | Following items to be purchased: - Bariatric beds - Bariatric patient Geri Chair - Bariatric commodes | Director, Inpatient and Emergency | Complete - 2021 |
|  | DRHC main entrance | Accessibility of main entrance: Space between the outside and inside doors is small Off-set doors difficult to maneuver with a wheelchair or stretcher. | Move outside entrance way further out onto the pavement to give more space between the two doors. Doors should be located on same side of entranceway. Replace main entrance doors with automatic doors that slide open | Director, Facilities Occupational Therapist | Complete – main doors have been replaced. |
|  | Dryden Area FHT | Accessibility of FHT main entrance doors | Investigate the FHT main entrance doors for accessibility | Director, Facilities Director, FHT | Complete – main doors are accessible |
|  | Dryden Area FHT | Review the need for a patient lift at the FHT | Patient lift purchased for the FHT | Director, FHT | Complete - 2021 |

| BARRIER TYPE | Location | DESCRIPTION OF BARRIER | STRATEGY to ADDRESS | LEAD PERSON/ PROGRESS | Timeline/ Status |
| --- | --- | --- | --- | --- | --- |
| Updated: 2022-2025 |  |  |  |  |  |
| Communication | Organization wide: Paging System | Staff/Patients/Visitors unable to hear paging system in certain areas of the hospital during a code | Determine what improvements and/or alternatives can be made to the paging system that can be used during an emergency. | Manager, IT | February 2024 |
|  | Organization wide: Vocera System | The Vocera system is not available in all parts of the hospital due to structure of the building | Determine what improvements and/or alternatives can be made to the Vocera system that can be used during an emergency. Ensure all staff are wearing and have access to a Vocera badge while on shift | Manager, IT Manager IT, Department Directors | February 2024 March 2023 |
|  | Organization- wide | Review the need for additional communication devices that maybe required or replaced due to age | Example: TTY, pocket talkers etc. | Director, Risk, Quality, Health/ Safety | October 2023 |
|  | Organization - wide | Translation services for staff – patient care | Implement Voyce translation services that can be utilized across the organization in all care settings. This will include sign language for those that require the service. | VP, Clinical Services, CPO | Winter 2023 |
|  | Organization – wide | Review the internal internet page for accessibility during an update process | Internal internet page will be overhauled completely with the integration of accessibility features included. | Communication and Board Liaison/ Manager, IT | Winter 2024 |
|  | Kitchen | Kitchen doorbell needs to be relocated for accessibility purposes | Doorbell at cashier needs to be at a lower level to be accessible for those in a wheelchair | Director, Dietary/ Facilities | February 2023 |
| Human Resources | Organization - wide | Review accommodation and return to work plan/procedure | Update the return to work and accommodation policies/ plans | Manager Employee Health, Clinical Education, Oncology | Fall 2025 |
| Physical Environment | Organization wide: automatic door timers | Across the organization the automatic door timers were identified as closing too quickly | Extend the timing of the automatic doors closing | Director, Facilities | Fall 2023 |
|  | Laboratory ticket dispenser | Ticket dispenser is currently too high for some patients | Lower the height of the ticket dispenser | Director, Laboratory/Facilities | May 2023 |
|  | Oncology | Oncology patient washroom requires an automatic door button | Update the Oncology washroom to include an automatic door button | Manager, Oncology Director, Facilities | Summer 2023 |
|  | West Wing Patient Bathroom | Location beside specialty clinic: review for accessibility | Lift bar Toilet height Door is heavy for those in a wheelchair | Rehab – OT/ Director, Facilities | Summer 2023 |
|  | Emergency Room | The following items were identified: - Bariatric stretcher (hi/low) - Bariatric wheelchair (additional chair to be considered) - Bathroom – beside quiet room - Extend door timer - Drop bar to support transfer from wheelchair to toilet | Review identified items with ER/IP Director to determine next steps | ER Director/ Facilities Director/ Rehab- OT | Summer 2024 |
|  | Specialty Day Care | Height of toilet in SDC patient bathroom | Toilet height | Director, Facilities | Summer 2023 |
|  | East Unit – Inpatient Department | The following items were identified: - LDRP/CCA shower is not accessible - The East Unit fire doors require hold backs as they are heavy to open and hold open when transferring a patient | Director, Facilities to address door holds on fire doors in the East Unit Shower would be updated on next renovation of area – Note: there are accessible showers in the East Unit if needed. | Director, Facilities/ ER/Rehab- OT | Winter 2024 |
|  | DRHC – Inpatient Unit/ Emergency Department | Determine what bariatric equipment is required for Inpatient Unit (East Unit) and/or Emergency Department | Following items to be purchased: - Bariatric beds - Bariatric lift | Director, Inpatient and Emergency | Complete - 2022 |
|  | Kitchen | Microwave/supplies in the cafeteria are too high for those in a wheelchair | Determine what alternatives can be made to ensure access to the microwave and supplies. Note: there is an accessible microwave in the cafeteria in a different location. The supplies remain to be addressed. | Dietary, Director | June 2023 |
|  | Dryden Area FHT | Transitions between carpeted area are creating a patient tripping hazard and difficult for patients with mobility issues to transverse | Update transition strips between areas to reduce staff or patient falls | Director, Facilities/ FHT | October 2024 |
|  | Dryden Area FHT | Lack of handrails on the walkway entrance to FHT | Review the need for a handrail along walkway and install if appropriate | Director, Facilities/ FHT | Summer 2023 |

Communication of the Plan

The 2022 - 2025 Multi-year Accessibility Plan will be posted on the internal and external websites of the Dryden Regional Health Centre.

The Multi-year Accessibility Plan has been produced using formatting that will facilitate conversion to alternate formats such as Braille or large font.  The plan will be made available in alternate format and/or with communication support, upon request.  You can make your request by contacting:

The Dryden Regional Health Centre

AODA Office

Attention: Katherine Campbell

58 Goodall Avenue, P.O. Box 3003 Dryden, ON P8N 2Z6

kcampbell@drhc.on.ca  - (807)223-8201 ext. 2268

Website: www.drhc.on.ca